## Master Sheet
# |  | Description | Action | Location | RMA Lead | Other RMAs | A-Z Version 2.0 ref | Date Added | Status | RAG
17/ | 02 | Churchtown walkover - walkover with Churchtown FLAG to identify all issues the FLAG have (09/05/2017) | - EA attending to map areas of concern for the community. | Churchtown | EA |  |  |  | Closed - 10/05/2017 | G
17/ | 04 | Direct correspondence 26/04/2017 - letter from member of FLAG regarding flooding issues at Ainspool | - The letter primarily refers to surcharging drains on Ainspool Lane. - No known update from Lancashire County Council on whether the issue is being addressed. | Churchtown | LCC |  |  |  | Letter sent 19/5/17 | G
17/ | 05 | Natural Flood Management application | EA attended a meeting with Churchtown FLAG on 26/04/2017. Agreed that a direct application would not be supported. However, Wyre Rivers Trust have agreed to include Ainspool on their application, which would mean opportunities mapping at Ainspool. 5/12/18 - Updated 'involving' column to include Wyre Rivers Trust & FLAG and re-opened. Update from Wyre Rivers Trust awaited | Churchtown | EA | WRT / FLAG /UU |  | updated 27/02/20 | Complete. Wyre Rivers Trust - Feasibility study now completed -additional funding is required for next phase. Wyre Rivers Trust are now looking for funding. WRT have installed 100 leaky dams and 3km of fencing on Smithy Beck on Abbeystead Estate. Additional works are planned for 2020/21. WRT also to look at works on the Ainspool. Funds have been raised by Churchtown FLAG. | G
17/ | 06 | EA Sandbox visit - invited FLAG to watch a demonstration of new sandbox technology from JBA consultant | Cancelled due to purdah | Churchtown | EA |  |  |  | Closed - 09/05/2017 | G
17/ | 08 | Churchtown pumping plan | - Draft plan has been drawn up and discussed with partners. - Pump locations agreed and main discharge points agreed. Additional discharge point to field adjacent Ainspool to be discussed with landowner. | Churchtown | WBC |  |  |  | Closed | G
17/ | 09 | Potential works adjacent to the River Wyre near Kirkland Bridge | - Topographical survey now complete and has been sent to landowner via Wyre Borough Council. | Churchtown | EA | WBC |  |  | Complete | G
17/ | 10 | Structural investigations of Ainspool banks | - Ground investigation works at Ainspool will investigate the possibility of porous material under the banks. - Report due by end of 2018 ? | Churchtown | EA |  |  |  | Ongoing | G
17/ | 11 | Unpermitted embankment | - EA Warning Letter issued | Churchtown | EA |  |  |  | Complete | G
17/ | 12 | Natural Flood Management Project updates | - Added to EA WFF Pre-meeting reports and presentations to WFF at key points. | Churchtown | EA |  |  |  | Closed | G
17/ | 13 | Topping up low spots, River Wyre | - Works programmed to top up three low spots on the River Wyre at Churchtown. - Provide update to group | Churchtown | EA |  |  |  | Complete | G
17/ | 14 | Kirkland Bridge Environmental Permit | - Issued | Churchtown | EA |  |  |  | Complete | G
17/ | 15 | Request for Funding for FLAG proposal | 4 Oct 17 EA received a phone call from member of FLAG asking whether any funding contribution would be available to assist with a FLAG proposal to contruct a bund upstream of Kirkland Bridge. 21 Feb 19 EA to vary permit and put notice onto property deeds regarding future maintenance. | Churchtown | EA | WBC | W17 | 2017-08-25 | Completed | G
18/ | 11 | Request for EA or multiple agency lecture on the different pathways to possible funding. | EA to suggest Wyre Flood Forum presentation with follow up section on TheFloodHub.co.uk | Churchtown | EA | WRT / NE |  | updated 27/02/20 | Complete. Presentation to Flood Forum proposed - no date yet planned. Presentation given at Wyre Flood Forum Dec 2019 | G
18/ | 17 | Potential to talk about DIY bund at National Conference | Churchtown FLAG made suggestion to EA nationally for Telford event (18-20 June 2019?) Call for content and speakers now open http://floodandcoast.com/ Action of FLAG to contact event organisers | Churchtown | FLAG |  |  | updated 05/09/19 | Closed | G
18/ | 18 | Kepple Lane development | Walkover planned with FLAG for 23 November to discuss concerns | Churchtown | EA |  |  | updated 27/02/20 | Complete. EA have inspected development with FLAG. UU to check tanks - can they be adopted by UU? Requires Developer to request adoption by UU. FLAG to approach Developer. UU S104 adoption in place | G
18/ | 19 | Abbeystead Estate Visit - Joint visit with EA / Churchtown FLAG to Abbeystead Estate | Planned for 6th December 2018 | Churchtown | EA |  |  | updated 05/09/19 | Completed. Query whether other Forum members wish to visit. | G
18/ | 20 | Portable Flood Defences - Request for any RMA comments in relation to portable defences | - CRMAs to provide comments including whether their organisation considered use in Churchtown, links to product information, any other relevant comments on storage / deployment etc | Churchtown | EA |  |  |  | Closed | G
18/ | 21 | Funding for Pumps - Would the EA (or others) look into buying equipment to pump water over roads in Churchtown (or other places) threatened with flooding ? | Response via the Wyre MSfWG Update 21/02/19 - EA have a number of pumps in their Sale depot although these are prioritised for EA assets; WBC have two high volume pumps. | Churchtown | EA | All |  | Update 06/06/19 | Complete Wyre Council has pumping plans for Churchtown and Sunnyside Terrace | G
18/ | 22 | Facebook Article re Comined Sewers and blocking off of CSOs to improve water quality | - EA response requested to email dated 08/12/18 | Churchtown | EA |  |  |  | Closed | G
18/ | 23 | Potential for funding for Landscaping / resilience on triangular piece of land where sandbags are stored (downstream / east of A586 - grid ref required) | - EA / RMA advice sought on any requirements / permits etc - Update 21/02/19 - discussed at MSfW, little benefit seen. | Churchtown | All |  |  |  | Closed | G
18/ | 36 | Flooding is possible query - can we change threshold ? | - Email 04/12/17 from FLAG " It was noted that the monitoring station on the River Brock at Roe Bridge frequently shows levels above the line saying minor flooding is possible. I think you said that the threshold of some of the monitoring stations was subject to review and I wondered whether this is such a station and whether the current threshold may be causing some unnecessary concern if it is indeed too low. Please would someone investigate this and let me know what I can report back to our FLAG members?" | Churchtown |  |  |  | updated 17/01/18 | Closed :- "In the absence of any FAL’s or FW thresholds 1.5m is good enough I guess so I will change the FIP to this." EA 040118 | G
19/ | 31 | What is the EA planned maintenance for the Ainspool downstream of road bridge | EA response: Scheduled for a cut in June and another cut in September. | Churchtown | EA |  | F6-F7 | updated 06/06/19 | Completed | G
19/ | 32 | Solar panels for telemetry at Kirkland Bridge were shaded by tree cover. Will this affect performance ? | EA response: There is also a 2 month battery supplied and these will be monitored and changed where required to ensure resilience of the monitoring. | Churchtown | EA |  | O6 | updated 06/06/19 | Completed | G
19/ | 33 | Could a staff gauge (red and white staff) be placed on near telemetry as a visual marker of depth ? | EA to update FLAG | Churchtown | EA |  | O6 | updated 05/09/19 | Completed. | G
19/ | 34 | On the path at the back of the church, that leads to the bridge over the river (Around grid ref H10) there is a wire fence protecting the bund where the original path was. Alternative path is slippy. Could metal webbing be placed on the bund to protect it from prior to fencing being removed | EA to update FLAG | Churchtown | EA |  | H10 | updated 28/11/19 | Ongoing. EA to remove fencing. Fencing has been removed. | G
19/ | 01 | Kirkland Bridge telemetry | - new site online. EA going on site in December 2018 to carry out survey to check to ensure levels are correct. - Plans to make the site permanent at start of 2019 as covered by Permitted Development - Update 21/02/19 - Permanent site by summer 2019 | Churchtown | EA |  |  | updated 05/09/19 | Completed. Telemetry now in place. Permanent status yet to be confirmed. | G
19/ | 24 | St Michaels FLAG and possibly other WFF members would like to have a guided visit to the Great Eccleston pumping station 52544 and the Churchtown sewage works. | UU to liaise with FLAG to arrange visit | Great Eccleston | UU |  |  | updated 05/09/19 | Site visit undertaken July 2019 | G
19/ | 37 | Back Lane - new development. | LCC / WBC to investigate local drainage to determine how site will discharge surface water. | Great Eccleston | WBC | LCC |  | 22/08/19 Updated 28/11/19 | WBC / LCC are objecting to surface water discharging to combined sewer. Require Developer to follow SuDS hierarchy for discharging surface water. WBC / LCC to undertake local survey to find alternative discharge point. Revised drainage layout agreed with Developer that removes surface water from foul sewer. | G
19/ | 38 | Copp Lane - new development. | WBC asked EA to undertake checks on York Drive pumping station. | Great Eccleston | WBC | LCC / EA |  | 22/08/19 Updated 28/11/19 | EA to check pumping station on York Drive. Station has been checked - all OK | G
19/ | 06 | Flooding of highway, Carr Lane, Hambleton | - Blocked gullies and/or watercourse near to Hambleton papershop - LCC (Highways) have investigated and will undertake works to redirect highway drainage. | Hambleton | LCC | UU, WBC |  | updated 27/02/20 | Ongoing. LCC to undertake works to improve local highway drainage. Works to commence in New Year. New sub-group of MSfW formed. Works to begin 2 March 2020 - See Sub-Group | A
19/ | 13 | Kiln Lane / Sherbourne Road, Hambleton - Local area has suffered numerous flooding incidents resulting in internal flooding to a number of properties. | UU to consider installation of new inspection chamber on culverted watercourse for easier access | Hambleton | All |  |  | updated 17/02/21 | Carried over from MSfW Hot Spots Ongoing - UU have inspected the banks of Wardleys watercourse and not located discharge point from culverted watercourse. - Investigation works may be required to ensure that water from local area can freely discharge to watercourse. - UU have excavated in footpath but encountered high water table. Will need to find alternate access point to survey culvert. UU to dye test piped watercourse to locate outfall. - WBC to undertake investigation into repeated flooding. - LCC to use sond to locate outfall to Wardleys watercourse - LCC have located and cleared outfall from private culverted watercourse. EA to look at additional works to improve flow. - Reopened following flooding 29 Sept. New sub-group of MSfW formed. - Inspection undertaken of local surface water drainage to establish connections and condition. Gullies on Kiln lane and Sherbourne Road cleared. - Private culvert and watercourse to north of Kiln Lane cleared by LCC. | A
19/ | 16 | Carr Lane, Hambleton - Flooding to properties from highway run-off. | LCC to clear highway gullies on Market Street and on Carr Lane in vicinity of Market Street to improve local highway drainage | Hambleton | LCC | WBC / EA |  | updated 27/02/20 | Carried over from MSfW Hot Spots. Ongoing - Gullies all done and to monitor after next rainfall - LCC to check all gullies on east side of Carr Lane for blockages - See 19/06 | G
21/ | 01 | Pauls Lane, Sandy Lane, Stoney Lane, Market Street | Surface water flooding during heavy rainfall - gullies surcharging onto highways |  | LCC | WBC, EA |  | 2021-02-03 |  | R
21/ | 02 | Bull Park Lane / Shard Lane | Highway flooding on Bull Park Lane |  | LCC | EA |  | 2021-02-03 |  | R
19/ | 10 | Derby Crescent, Inskip - Surface water flooding to residential street. Foul and surface water misconnections in local drainage leading to foul in street |  | Inskip | LCC |  |  | 2019-02-20 | Carried over from MSfW Hot Spots Completed - UU have inspected and report misconnection of highway drainage and local residential property. - LCC to fix connection issues; UU to contact resident to resolve misconnection. - Resident has been advised and will undertake misconnection works. - LCC to resolve misconnection of highway drainage | G
20/ | 05 | Carr End Lane, Stalmine. Regular flooding of highway close to Lynwood Drive. Concerns have been raised about the proposed housing development adjacent to the site. | Making Space for Water Group to hold a walkover of Stalmine issues with new FLAG. Date to be organised | Stalmine | ALL |  |  | 2020-02-27 | MSfW to organise walkover with FLAG | A
17/ | 01 | EA Sandbox visit - invited FLAG to watch a demonstration of new sandbox technology from JBA consultant | - Cancelled due to pre-election period following advice from C&E | St Michaels |  |  |  |  | Closed - 08/05/2017 | G
17/ | 03 | Leaking flood gate at Catterall basin (near the footbridge) | - Contractors have visited the site but no definitive timescale has been set. EA to follow up. - Update - Project Manager confirmed that this work has now been complete and email update to St Michaels Group has been sent out to reflect this | St Michaels |  |  |  |  | Closed 05/10/17 | G
17/ | 07 | Tarnacre - requested a meeting with Paul Flintoff and all relevant agencies regarding the flooding issues at Tarnacre, the bunds, the quarrying activities etc. | - EA received correspondence via Wyre Borough Council and directly to EA. - EA questions have been directed to C&E | St Michaels |  |  |  |  | Ongoing | G
17/ | 17 | Embankment issues - Rabbit holes in the south bank of Wyre between the Coppice and Long Meadow at St Michael's (05/04/2017) | - Update FLAG on any actions and schedules. If no work planned or monitoring just feed that back. - 12/7/18 - Due to be carried out by the end of 2018 - 05/11/18 - EA confirmed works are complete and machine being removed from site | St Michaels |  |  | Q18 |  | Complete | G
17/ | 18 | Natural Flood Management Project - Alison Whalley to give a presentation at the next Wyre Flood Forum | - AW to give presentation at the June 2017 Wyre Flood Forum. | St Michaels |  |  |  |  | Complete 29/06/2017 | G
18/ | 09 | Warrington forecasting centre - requested a visit to forecasting colleagues in the Warrington office | Update from 16/1/18 meeting. Change to WFF Presentation Update 06/02/19 - Book for March or June 2019 if possible | St Michaels | EA |  |  | updated 28/11/19 | Completed. Presentation to Flood Forum planned for Sept 2019. Warrington presentation can be noted as completed since Sept 19 WFF. A representative of the forecasting group is visiting St Michaels FLAG in late October to discuss how St M FLAG can assist their work. Will also discuss methods of estimation of river flow and capacity in relation to rainfall, ground saturation, pinch points such as bridges etc | G
18/ | 10 | River level measurements - inconsistency in quoting water height at Catterall to issue flood warnings (seems not be in AOD) | - The measurements quoted in our manual for the Catterall flood basin are not in AOD, whereas measurements for other gauges on the Wyre are in AOD. This was the way it was set up originally but now we don't tend to use it i.e. this is just a legacy arrangement and there are no immediate plans to change it. However it will be discussed with AP / Field Teams etc. Update 16/01/18 - This has also been flagged up as a recommendation by Wyre BC in that consistency using AOD would make more sense for FAS tele-cons etc - Update 9/7/18 - Understand that there are multiple data feed for this locations and colleagues are looking into this. Any changes will be updated to the Community Group | St Michaels |  |  |  |  | see 18/55 | G
18/ | 24 | Basins training dates - requested the dates of training carried out at the basins | - As training dates change EA will propose to send retrospective update at each WFF. (Stored in basin visits folder) - Supply for each WFF | St Michaels |  |  |  |  | Supply for each WFF | G
18/ | 25 | Catterall Flood Basin site visit - requested a follow up visit to Catterall Flood Basin | St Michaels FLAG to ask community if there are any interested parties for this. 04/02/19 - NB from EA to arrange a date in April/May to suit FLAGs Update 28/02/19 - EA to arrange meeting with FLAG and MEICA Team - likely to be April / May 2019 | St Michaels | EA |  |  | Updated 27/02/20 | Completed. NB to arrange visit. | G
18/ | 27 | A-Z Grid Maps for the Parish | - Map to be updated to cover whole Parish. EA to get approval from FLAG. Once approved these maps will need to go to Wyre BC to be included in the Flood Risk Summary sheet. - EA to upload electronic copy to IM Toolbox with version control. - Additional action to consider adding key features on to the maps in consultation with St Michaels FLAG - v 2.0 complete | St Michaels | EA | WBC |  |  | Complete v2.0 | G
18/ | 28 | Upper and Mid Wyre Review | - St Michaels FLAG strongly against this review being signed off before they have had chance to see the final version and feel that this was requested / agreed at the Wyre Flood Forum. They want a final version circulated to FLAGs and Cllr Berry and EA representation from someone involved with the review at the next Wyre Flood Forum | St Michaels | EA |  |  |  |  | G
18/ | 29 | Snakes & Ladders / Lancaster Uni (C & YP) | - EA to ask National colleagues for an update on this. Actioned on 17 Jan 2018. - 05/11/18 - If online resource becomes available this should be added to TheFloodHub.co.uk -08/11/18 - Online link http://wp.lancs.ac.uk/cyp- floodrecovery/our-outputs/flood-snakes-and-ladders/ | St Michaels | EA |  |  | 2018-01-17 | Closed | G
18/ | 30 | Maintenance Enquiry Rivermede and Catterall Basin | - FLAG had requested maintenance update. EA confirmed that team was going on site on 290917 and this was fed back to FLAG / resident. EA provided update once works had been completed | St Michaels | EA |  |  | Updated 29/09/17 | Completed | G
18/ | 31 | St Michaels Walkover | - Offer from St MichaelsFLAG for EA to attend a site walkover. | St Michaels |  |  |  | updated 17/01/18 | Complete 13/04/18 | G
18/ | 33 | Upper & Mid Wyre Review- follow-up for FLAG | - Email 4/12/17 from FLAG "I believe there will be items to follow up with your colleagues arising from our review of the report and when it is convenient for you please ask them to propose some dates when we can discuss anything which requires resolution." - Update on 17 Jan 2018. Meeting confirmed for 10am Monday 19th February at St Michaels. | St Michaels |  |  |  | updated 17/01/18 | Completed 19/02/18 | G
18/ | 34 | Brock embankment - potential 'trickling' through repaired section | - Email 04/12/17 from FLAG "At our FLAG meeting some members suggested that the repairs made to the Brock Bank following the floods of Dec 2015 may still be “trickling”. Apparently the adjacent field has had an unusual amount of standing water in it at times of high river level since then. I am not able to comment on whether the “trickling” theory is correct but I have seen the water in the field." - 12/7/18 - EA to check whether this section was sheet-piled and if so whether it is the field drains that may have damaged - 05/11/18 - Project Manager to investigate this week and report back to FLAG | St Michaels | EA |  | W18 or X17 | updated 28/11/19 | Ongoing:- AP/Field team to monitor. This is the first report we have had regarding the site. The field drains for the whole area drain under the floodbank at this point and if the river is high, ponding in the field should be expected. Ongoing - EA to chase this up FLAG is satisfied with this response so could be marked as completed. | G
18/ | 35 | Details of EA visual Inspection | - Email 04/12/17 from FLAG "One of our members reported meeting an employee of the EA walking on the river banks during the week before our meeting and was told that he was making a visual inspection of the state of the river banks etc. Would it be possible please to have a note of his observations in relation to our Parish?" | St Michaels |  |  |  | updated 17/01/18 | Closed :- This is normal in the lead up to any period of forecast rain. The operative would have been looking for any signs of bank deterioration in the form of vermin damage, livestock damage or slumping of the banks. None was reported at the time | G
18/ | 37 | Myerscough College Embankment | - Email 04/12/17 from FLAG "A question was asked about the effect of recent flood banks installed by Myerscough College on the volatility of the River Brock, which you staff have previously said has increased in recent years. Is it possible to have any comments on this please?" update on 17 Jan 2018 - outside parish boundary but on Paul's phone for reference - 12/07/18 - In theory this shouldn't increase flood risk to properties given the rural location but Asset Performance Team now aware. - 05/11/18 - Agreed that although not an immediate priority this should remain on log to be picked up if and when resources to investigate further are obtained. The unpermitted bund and impacts downstream remain the modelling priority for the group. - Update 28/02/19 - EA Asset management Team to investigate | St Michaels |  |  | A18 - A19 | updated 27/02/20 | Completed. EA to check whether permit is required or issued. FLAG comment - There may be two issues here. The first being any bunds installed by Myerscough college as part of their extensions. FLAG is now aware of the location or implications of these. The second issue is a relatively new bund which we believe is unpermitted and Wyre Borough Planning Dept have been asked several months ago to investigate. This bund is near Roe Bridge. Need to add a comment as to whether the EA have discovered whether a permit is required and/or has been issued. - EA, case can be closed | G
18/ | 38 | UMWR Scoping Meeting Request | - St Michaels FLAG asked for a follow-up meeting to the meeting that took place on the 19th Feb 2018. This is to finalise a 'sign-off' of the review and also to discuss the scope of the next steps - 09/07/18 - David Blake received answer from consultant re do nothing and do minimum potential error - info was correct | St Michaels | EA |  |  | 2018-02-19 | Complete - Email sent out on 11 July 2018 | G
18/ | 39 | Walkover - general comment | - EA to organise someone from Lancashire County Council to call landowner to discuss permissions required to carry out works on an Ordinary Watercourse in St Michaels on land north of the River Wyre. | St Michaels | EA |  |  | 2018-05-09 | Complete 09/05/18 | G
18/ | 40 | Photo 5 from walkover | - TG to find out why the contractor had done this and to challenge the contractor to remedy this. - Update 23 May 2018 - Chipper will be used on site as soon as bird nesting season is complete. - 09/07/18 - Planned to be carried out by EA field team may have been completed - 05/11/18 - Believed to be complete FLAG / EA field teams to confirm prior to closing this | St Michaels | EA |  |  | 2018-05-09 | Closed 06/02/19 | G
18/ | 44 | Debris left on site - photo 19 | - At the location of photo 19 there was disappointment at the state in which the contractors had left the site. Both debris and a soil mound had been left clearly visible so EA said they would report this back as well. - 15/5/18 - Project Manager has flagged this up together with the 'defect' of manhole cover sitting proud of the group - 05/11/18 - Project Manager - this manhole cover was level with the ground originally but 'back-flow' scoured land around it. This 'defect' will be investigated again this week during site visit | St Michaels | EA |  | X18 | updated 06/03/20 | Not causing flood risk- advise to be closed down. | G
18/ | 58 | At our meeting last night, it was noted that nothing appears to have been done about an issue with the river bank in the woods at the Old House, Hall Lane, St Michaels on Wyre. This was identified as a problem some 3 years ago. Do you know whether this is still on the radar please and if not, would there be someone else dealing with it? | - 17/01/19 - Check with PN at next meeting and update enquirer re email on 16/1/19 - 06/02/19 - PB emailed enquirer to advise future enquiries to be sent to the FLAG so that regular updates can be obtained via MSfW | St Michaels |  |  |  | 2018-11-06 | Closed | G
19/ | 02 | Flood outline for Tarnacre from August 2016 The flooding mechanism from the main river has been demonstrated by video and by photograph so please update the flood outline map. | - Information provided by FLAG member to update the flood outline from August 2016. - 06/02/19 - Re-opened as PF has provided a photo showing the location flooded. Needs to be covered at MSfW - Update 21/02/19 - Group aware of the issue. Flooding mechanism has not yet been proven | St Michaels | EA | All |  | Updated 27/02/20 | Ongoing. Flood outline map needs to be updated. - EA - no evidence that flooding is from watercourse. EA have no plans to update their flood maps. | G
19/ | 03 | Issues 26 - 36 picked up via St Michaels Walkover. The figure of £2.6BN of government money was mentioned following the December 2015 floods – where did that money go and how much was spent in Lancashire? | - Not sure of exact amount but understand that money went to Cumbria and Yorkshire but not to Lancashire - 06/02/19 - A proportion of that money was spent in Lancashire on embankment and asset repairs done in 2016 after the December 2015 floods. | St Michaels | EA |  |  | 2019-02-04 | Closed 06/02/19 | G
19/ | 04 | EA actions wrt Hamilton House Farm Bund | - Email from St Michaels FLAG on 280118 requesting representative to next WFF to give explanation of EA actions re this one. - 09/07/18 - EA to try and arrange representative - 12/07/18 - EA have offered to have this meeting outside the flood forum possibly before the Dec Flood Forum Does this sound ok ? Alternatively we can look to arrange a separate meeting - 05/11/18 - To be transferred to MSfW I&A log and receive input from Wyre BC / LCC where applicable re potential enforcement. - 04/02/19 - EA responded to resident complaint about Hamilton House Farm bund | St Michaels | EA |  |  | 2019-02-04 | Closed | G